## Product Backlog
Fitness & Workout Tracker — Product Backlog (Group 11)
ID | Epic | User Story | Acceptance Criteria | Priority | Estimate (Story Points) | Sprint | Release | Status
PB-01 | Technical Foundation | Set up Git repository with branch protection As the team, we want a Git repo with branch protection on main so that code is reviewed before it is merged. | • Git repo created and all team members have access • Branch protection enabled on main • Changes reach main only through pull requests | 1 | 1 | Sprint 1 | R1 – MVP | In Progress
PB-02 | Technical Foundation | Set up CI pipeline As the team, we want a CI pipeline so that every change is built and tested automatically. | • CI builds on every pull request • CI runs the automated tests • Build and test result shown on the pull request | 2 | 2 | Sprint 1 | R1 – MVP | In Progress
PB-03 | Technical Foundation | Set up database and hosting with starter page As the team, we want the database and hosting environment live so that we can ship increments every sprint. | • Database live and reachable by the app • Hosting environment live • Starter page deployed to test URL | 3 | 2 | Sprint 1 | R1 – MVP | In Progress
PB-04 | User Accounts | Registration form with validation As a new user, I want to register with my email and password so that my data is saved. | • Valid email format required • Password at least 8 characters • Account created on valid submission | 4 | 2 | Sprint 1 | R1 – MVP | Done
PB-05 | User Accounts | Secure password storage and duplicate email handling As a new user, I want my password stored securely and duplicate accounts prevented so that my data is protected. | • Duplicate email rejected with message • Password stored hashed (bcrypt) | 5 | 1 | Sprint 1 | R1 – MVP | Done
PB-06 | User Accounts | User login As a user, I want to log in so that only I can see my data. | • Correct credentials open the dashboard • Wrong password shows an error | 6 | 2 | Sprint 1 | R1 – MVP | Done
PB-07 | User Accounts | User logout As a user, I want to log out so that no one else can see my data on a shared device. | • Logout ends the session • Protected pages redirect to login after logout | 7 | 1 | Sprint 1 | R1 – MVP | Done
PB-08 | User Accounts | Create and edit fitness profile As a user, I want to set up my profile so that the app fits my level and goal. | • Age, height, weight, fitness level and goal saved • Profile editable later • kg/lb units selectable | 8 | 3 | Sprint 1 | R1 – MVP | Done
PB-09 | Exercise Library | Seed preset exercise library As a user, I want a preset library of exercises so that I do not have to enter them myself. | • 50+ exercises seeded • Each stores name, muscle group, equipment and instructions | 9 | 2 | Sprint 1 | R1 – MVP | Done
PB-10 | Exercise Library | Browse exercises grouped by muscle group As a user, I want to browse exercises by muscle group so that I can pick what to train. | • Exercises grouped by muscle group • Each shows name, muscle group and equipment | 10 | 2 | Sprint 1 | R1 – MVP | Done
PB-11 | Exercise Library | View exercise instructions As a user, I want to open an exercise and read its instructions so that I can perform it correctly. | • Selecting an exercise shows its instructions • Detail view shows muscle group and equipment | 11 | 1 | Sprint 1 | R1 – MVP | Done
PB-12 | Exercise Library | Search exercises by name As a user, I want to search exercises by name so that I find one fast. | • Search by name • Results update in under 1 second | 12 | 1 | Sprint 1 | R1 – MVP | Done
PB-13 | Exercise Library | Filter exercises by muscle group and equipment As a user, I want to filter exercises so that I can narrow down to what I can train today. | • Filter by muscle group • Filter by equipment • Filters work together with search • Results update in under 1 second | 13 | 2 | Sprint 1 | R1 – MVP | Done
PB-14 | Workouts & Scheduling | Create and name a workout template As a user, I want to create a named workout template so that I can reuse my routines. | • Name a template • Template saved to my account | 14 | 2 | Sprint 2 | R1 – MVP | To Do
PB-15 | Workouts & Scheduling | Add, reorder and remove exercises in a template As a user, I want to build up a template's exercises so that it matches my routine. | • Add exercises from the library • Set target sets/reps for each exercise • Reorder and remove exercises | 15 | 2 | Sprint 2 | R1 – MVP | To Do
PB-16 | Workouts & Scheduling | Edit and delete workout templates As a user, I want to edit and delete templates so that my routines stay up to date. | • Edit an existing template • Delete a template | 16 | 1 | Sprint 2 | R1 – MVP | To Do
PB-17 | Workout Logging | Start a workout from a template or blank As a user, I want to start a workout from a template or a blank session so that I can begin logging. | • Start from a template or blank • Template exercises pre-loaded into the session | 17 | 2 | Sprint 2 | R1 – MVP | To Do
PB-18 | Workout Logging | Log sets, reps and weight As a user, I want to log sets, reps and weight during a workout so that I record what I did. | • Add sets with reps and weight • Sets listed under each exercise | 18 | 2 | Sprint 2 | R1 – MVP | To Do
PB-19 | Workout Logging | Finish and save workout session As a user, I want to finish my workout so that the session is saved to my history. | • Finish saves session • Session stores date and duration | 19 | 2 | Sprint 2 | R1 – MVP | To Do
PB-20 | Workout Logging | Keep in-progress workout after page refresh As a user, I want my unfinished workout to survive a page refresh so that I do not lose my logged sets. | • In-progress workout survives page refresh • Reopening the app returns to the unfinished workout | 20 | 2 | Sprint 2 | R1 – MVP | To Do
PB-21 | History & Data | View workout history list As a user, I want to see my past workouts so that I can review my training. | • List sorted newest first • Open a session to see all sets | 21 | 2 | Sprint 2 | R1 – MVP | To Do
PB-22 | History & Data | Filter history by date range As a user, I want to filter my history by date so that I can find a specific period. | • Filter by date range • List shows only matching sessions | 22 | 1 | Sprint 2 | R1 – MVP | To Do
PB-23 | Workout Logging | Edit logged sets in past sessions As a user, I want to edit logged sets so that my log stays accurate. | • Edit any logged set • Changes saved to the session | 23 | 1 | Sprint 2 | R1 – MVP | To Do
PB-24 | Workout Logging | Delete past sessions As a user, I want to delete past sessions so that mistaken entries do not stay in my log. | • Delete asks for confirmation • Deleted session removed from history | 24 | 1 | Sprint 2 | R1 – MVP | To Do
PB-25 | Workout Logging | Add notes to past sessions As a user, I want to add notes to past sessions so that I can record how it went. | • Notes up to 500 characters • Notes shown when the session is opened | 25 | 1 | Sprint 2 | R1 – MVP | To Do
PB-26 | Body Metrics | Log body weight As a user, I want to log my body weight so that I can track change over time. | • One entry per date • Edit or delete entries • Entries listed in history | 26 | 2 | Sprint 2 | R1 – MVP | To Do
PB-27 | User Accounts | Request password reset email As a user, I want to request a reset link by email so that I can get back in if I forget my password. | • Reset link emailed • Link expires after 1 hour | 27 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-28 | User Accounts | Set new password from reset link As a user, I want to set a new password from the reset link so that I can log in again. | • Valid link lets the user set a new password • Old password stops working after reset | 28 | 1 | Sprint 3 | R2 – Feature complete | To Do
PB-29 | Goals & Progress | Create fitness goals As a user, I want to set goals so that I have something to aim for. | • Goal types: target weight, workouts per week, lift PR • Goals saved to my account | 29 | 3 | Sprint 3 | R2 – Feature complete | To Do
PB-30 | Goals & Progress | Show goal progress As a user, I want to see how far along each goal is so that I stay motivated. | • Progress shown as % complete • Updates when new data is logged | 30 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-31 | Goals & Progress | Body weight progress chart As a user, I want a body weight chart so that I can see my change over time. | • Chart of body weight over time | 31 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-32 | Goals & Progress | Weekly volume chart As a user, I want a weekly volume chart so that I can see my training load. | • Chart of weekly volume | 32 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-33 | Goals & Progress | Personal record chart per exercise As a user, I want a PR chart for each exercise so that I can see my lifts improving. | • Chart of PR per exercise • Exercise selectable | 33 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-34 | Goals & Progress | Chart time range selector As a user, I want to change the time range on my charts so that I can see short and long-term progress. | • Ranges: 4 weeks, 3 months, all time • Applies to all charts | 34 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-35 | Goals & Progress | Dashboard: workouts this week As a user, I want to see my workouts this week so that I know where I stand at a glance. | • Shows workouts this week | 35 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-36 | Goals & Progress | Dashboard: goal progress As a user, I want to see my goal progress on the dashboard so that I know how close I am. | • Shows goal progress | 36 | 1 | Sprint 3 | R2 – Feature complete | To Do
PB-37 | Goals & Progress | Dashboard: next scheduled and last workout As a user, I want to see my next scheduled and last workout so that I know what is coming up and what I did last. | • Shows next scheduled workout • Shows last workout | 37 | 2 | Sprint 3 | R2 – Feature complete | To Do
PB-38 | Workout Logging | Show last performance while logging As a user, I want to see my last weight and reps while logging so that I know what to lift. | • Previous session's sets shown beside each exercise | 38 | 3 | Sprint 3 | R2 – Feature complete | To Do
PB-39 | Workout Logging | Log cardio session As a user, I want to log cardio so that all my training is in one place. | • Duration, distance and calories • Session saved with date | 39 | 2 | Sprint 4 | R2 – Feature complete | To Do
PB-40 | Workout Logging | Cardio units and weekly totals As a user, I want my cardio in my preferred units and in my weekly totals so that my numbers add up. | • km/mi units • Counted in weekly totals | 40 | 1 | Sprint 4 | R2 – Feature complete | To Do
PB-41 | Exercise Library | Create custom exercise As a user, I want to add custom exercises so that I can log anything I do. | • Name, muscle group and equipment • Saved to my exercise library | 41 | 2 | Sprint 4 | R2 – Feature complete | To Do
PB-42 | Exercise Library | Custom exercises private and usable in templates As a user, I want my custom exercises kept private and usable in templates so that I can plan with them. | • Visible only to the creator • Usable in templates | 42 | 1 | Sprint 4 | R2 – Feature complete | To Do
PB-43 | Workouts & Scheduling | Assign workout templates to days As a user, I want to schedule workouts on a weekly calendar so that I plan my week. | • Weekly calendar view • Assign a template to a day | 43 | 2 | Sprint 4 | R2 – Feature complete | To Do
PB-44 | Workouts & Scheduling | Repeat scheduled workouts weekly As a user, I want scheduled workouts to repeat so that I do not re-plan every week. | • Repeat weekly option • Repeats appear on following weeks | 44 | 2 | Sprint 4 | R2 – Feature complete | To Do
PB-45 | Workouts & Scheduling | Mark scheduled workouts done automatically As a user, I want scheduled workouts marked done when I log them so that my plan stays current. | • Marked done when logged | 45 | 1 | Sprint 4 | R2 – Feature complete | To Do
PB-46 | Admin | Admin-only access to exercise management As an admin, I want a restricted management page so that only admins can change the exercise library. | • Admin-only page • Non-admins blocked | 46 | 2 | Sprint 4 | R2 – Feature complete | To Do
PB-47 | Admin | Admin: add and edit preset exercises As an admin, I want to add and edit preset exercises so that content stays accurate. | • Add exercises • Edit exercises | 47 | 2 | Sprint 4 | R2 – Feature complete | To Do
PB-48 | Admin | Admin: remove preset exercises As an admin, I want to remove preset exercises so that outdated content is gone. | • Remove exercises | 48 | 1 | Sprint 4 | R2 – Feature complete | To Do
PB-49 | User Accounts | Delete account and personal data As a user, I want to delete my account and data so that my privacy is protected. | • Confirmation step required • All personal data removed from database | 49 | 3 | Sprint 4 | R2 – Feature complete | To Do
PB-50 | Workout Logging | Rest timer between sets As a user, I want a rest timer between sets so that I rest the right amount. | • Starts when a set is completed • Default 90 s, adjustable • Alert when time is up | 50 | 2 | Sprint 4 | R2 – Feature complete | To Do